## Dashboard
JobStrike UAE — Project Plan
Launch Date | Friday, May 1, 2026
Days until launch (from April 11) | 20
Phases
Phase | Dates | Duration | What Happens
Phase 0: Preparation | April 11–13, 2026 | 3 days | Weekend before validation
Phase 1: Validation Sprint | April 14–18, 2026 | 5 days | Customer interviews + ad tests + ATS feasibility
Phase 2: Go/No-Go Decision | April 19, 2026 | 1 day | Decision brief + commitment
Phase 3: Build Sprint | April 20–30, 2026 | 11 days | Solo founder MVP build
Phase 4: LAUNCH | May 1, 2026 | 1 day | Soft launch to waitlist + LinkedIn post
Phase 5: Post-Launch Iteration | May 2–31, 2026 | 30 days | Weekly Office Hours + moat feature ship
Key Numbers
Total budget (validation + build + launch) | AED 19,000
Validation budget only | AED 1,500
Subscription price | AED 49/month or AED 399/year
Free trial | 14 days
Month 1 target users | 300 total / 25 paying
Month 6 target users | 5,000 total / 400 paying
Break-even target month | Month 5–7 (Sept–Nov 2026)
UAE employer universe (from Apollo) | 163,016 companies across 5 sectors
Actively-hiring UAE companies (from Apollo) | 989 verified
HR decision-makers identified (from Apollo) | 299 at top 100 employers

## Timeline
# | Phase | Task (plain English) | Start Date | End Date | Days | Owner | Status | Depends On | Outcome / Deliverable
1 | Phase 0: Prep | Register jobstrike.ae domain + set up founder email | 2026-04-11 | 2026-04-11 | 1 | Founder | today | - | Domain live, founder@jobstrike.ae working
2 | Phase 0: Prep | Build 1-page landing site on Vercel with waitlist + fake-door CTA | 2026-04-12 | 2026-04-12 | 1 | Founder | pending | 1 | Landing page at jobstrike.ae
3 | Phase 0: Prep | Apply to Adzuna, Jooble, CareerJet publisher APIs | 2026-04-13 | 2026-04-13 | 1 | Founder | pending | 2 | API applications submitted
4 | Phase 0: Prep | Finalize interview guide + ad creative + LinkedIn DM template | 2026-04-13 | 2026-04-13 | 1 | Founder | pending | - | Ready for Day 1
5 | Phase 1: Validation | Day 1: Launch LinkedIn + FB ads, send 20 DMs, do 2 interviews | 2026-04-14 | 2026-04-14 | 1 | Founder | pending | 4 | Ads live, 2 interviews recorded
6 | Phase 1: Validation | Day 2: 3 interviews, iterate ad creative, send 15 more DMs | 2026-04-15 | 2026-04-15 | 1 | Founder | pending | 5 | 5 interviews cumulative
7 | Phase 1: Validation | Day 3: 3 interviews, start ATS feasibility study (5 cos) | 2026-04-16 | 2026-04-16 | 1 | Founder | pending | 6 | 8 interviews cumulative
8 | Phase 1: Validation | Day 4: Final 2 interviews, complete ATS study (15 more cos) | 2026-04-17 | 2026-04-17 | 1 | Founder | pending | 7 | 10 interviews + 20-company ATS study
9 | Phase 1: Validation | Day 5: Synthesis + decision brief writing | 2026-04-18 | 2026-04-18 | 1 | Founder | pending | 8 | Decision brief draft
10 | Phase 2: Decision | Go/No-Go decision + publish LinkedIn honesty post | 2026-04-19 | 2026-04-19 | 1 | Founder | pending | 9 | Decision committed publicly
11 | Phase 3: Build | Day 1 (Mon Apr 20): Next.js + Supabase scaffold + magic link auth | 2026-04-20 | 2026-04-20 | 1 | Founder | pending | 10 | Signup works
12 | Phase 3: Build | Day 2 (Tue Apr 21): Adzuna + Jooble integration + landing query form | 2026-04-21 | 2026-04-21 | 1 | Founder | pending | 11 | Visitors see real jobs
13 | Phase 3: Build | Day 3 (Wed Apr 22): Greenhouse + Lever ATS adapters + dedup | 2026-04-22 | 2026-04-22 | 1 | Founder | pending | 12 | Direct-from-employer jobs flowing
14 | Phase 3: Build | Day 4 (Thu Apr 23): Feed UI + city filter + job detail page | 2026-04-23 | 2026-04-23 | 1 | Founder | pending | 13 | Browsable feed with filters
15 | Phase 3: Build | Day 5 (Fri Apr 24): CV upload + parse + OpenAI banded fit score | 2026-04-24 | 2026-04-24 | 1 | Founder | pending | 14 | Fit score live
16 | Phase 3: Build | Day 6 (Sat Apr 25): Resend email alerts + PDPL consent flow | 2026-04-25 | 2026-04-25 | 1 | Founder | pending | 15 | Users get daily digest
17 | Phase 3: Build | Day 7 (Sun Apr 26): Ghosting Shield auto-log + Stripe integration | 2026-04-26 | 2026-04-26 | 1 | Founder | pending | 16 | Paying flow end-to-end
18 | Phase 3: Build | Day 8 (Mon Apr 27): User dashboard + profile + query management | 2026-04-27 | 2026-04-27 | 1 | Founder | pending | 17 | Dashboard feels real
19 | Phase 3: Build | Day 9 (Tue Apr 28): Founder Office Hours (Calendly + Zoom) + status banner | 2026-04-28 | 2026-04-28 | 1 | Founder | pending | 18 | Bookings working
20 | Phase 3: Build | Day 10 (Wed Apr 29): Full QA + mobile responsive pass + Sentry | 2026-04-29 | 2026-04-29 | 1 | Founder | pending | 19 | No known bugs
21 | Phase 3: Build | Day 11 (Thu Apr 30): Final deploy + launch-day content + waitlist email | 2026-04-30 | 2026-04-30 | 1 | Founder | pending | 20 | Go-live flag ready
22 | Phase 4: LAUNCH | LAUNCH DAY: Email waitlist + LinkedIn post + Facebook UAE groups | 2026-05-01 | 2026-05-01 | 1 | Founder | pending | 21 | First 50 signups by EOD
23 | Phase 5: Post-Launch | Week 1 iteration — bug fixes + user feedback | 2026-05-02 | 2026-05-08 | 7 | Founder | pending | 22 | Week 1 stability
24 | Phase 5: Post-Launch | First Founder Office Hours live session | 2026-05-04 | 2026-05-04 | 1 | Founder | pending | 22 | First group call
25 | Phase 5: Post-Launch | Ship First-Batch Indicator feature | 2026-05-09 | 2026-05-15 | 7 | Founder | pending | 23 | Moat feature 1 live
26 | Phase 5: Post-Launch | Ship Salary X-ray + public /salaries page | 2026-05-16 | 2026-05-22 | 7 | Founder | pending | 25 | Moat feature 2 live + SEO play
27 | Phase 5: Post-Launch | Ship UAE Hiring Pulse public dashboard | 2026-05-23 | 2026-05-29 | 7 | Founder | pending | 26 | Press bait + SEO
28 | Phase 5: Post-Launch | Month 1 review: first 100 paying users | 2026-05-30 | 2026-05-31 | 2 | Founder | pending | 27 | 100 paying / AED 4,900 MRR

## Budget
Category | Line Item | AED | USD | Phase | Notes
Validation | LinkedIn ads (5 days) | 500 | 136 | Phase 1 | UAE targeting, mid-career roles
Validation | Facebook + Instagram ads (5 days) | 300 | 82 | Phase 1 | Expat lookalike audiences
Validation | Interview thank-you gifts (10 x AED 30) | 300 | 82 | Phase 1 | Careem Pay vouchers
Validation | Domain + hosting (landing page) | 200 | 55 | Phase 0 | jobstrike.ae + Vercel hobby
Validation | Misc (Canva, translations, contingency) | 200 | 55 | Phase 1 | -
Infrastructure | Supabase (pro plan) | 1000 | 272 | Phase 3 | ~USD 25/mo × 3 months
Infrastructure | Vercel | 0 | 0 | Phase 3 | Hobby tier suffices at launch
Infrastructure | OpenAI API (3 months) | 500 | 136 | Phase 3 | GPT-4o-mini fit scoring
Infrastructure | Resend email | 0 | 0 | Phase 3 | Free tier 3k emails/mo
Infrastructure | Sentry error monitoring | 0 | 0 | Phase 3 | Free tier
Infrastructure | Domain SSL, DNS, misc | 500 | 136 | Phase 3 | -
Legal & Compliance | PDPL + scraping ToS legal review (2h UAE lawyer) | 2500 | 680 | Phase 3 | Before launch
Marketing (Month 1-3) | LinkedIn organic founder voice | 0 | 0 | Phase 5 | Founder time
Marketing (Month 1-3) | Paid LinkedIn ads Month 2-3 | 2000 | 545 | Phase 5 | After unit economics validated
Marketing (Month 1-3) | Content creation (Canva Pro, misc) | 700 | 190 | Phase 5 | -
Marketing (Month 1-3) | Referral incentives pilot | 1000 | 272 | Phase 5 | -
Contingency | 25% buffer | 4500 | 1225 | All | Unplanned expenses
TOTAL |  | 19000 | 5200 |  | Upfront + Month 1-3 operating

## Milestones
Date | Milestone | Status | Why It Matters
2026-04-11 | Spec v2.2 + Validation Plan + Business Plan locked | today | Documentation commit before any money is spent
2026-04-13 | Landing page live, publisher APIs applied | pending | Validation starts Tuesday
2026-04-14 | Validation Sprint Day 1 — ads live + first interviews | pending | Customer discovery begins
2026-04-18 | Validation Sprint Day 5 — decision brief | pending | Data collection complete
2026-04-19 | GO / NO-GO decision | pending | Commitment gate
2026-04-20 | Build Sprint Day 1 | pending | Code begins
2026-04-30 | Build Sprint Day 11 — production deploy | pending | Ready to launch
2026-05-01 | PUBLIC LAUNCH | pending | The big day
2026-05-04 | First Founder Office Hours session | pending | Proof the moat works
2026-05-31 | Month 1 review — 100 paying users target | pending | Unit economics check-in
2026-08-31 | Month 4 review — break-even path | pending | Financial gate
2026-11-01 | Concierge employer pilot launches (10 companies) | pending | Month 6 unlock
2027-05-01 | Year 1 anniversary — first external hire | pending | Scale begins

## Launch_Runbook
Time (Gulf) | Action | Owner | Status | Notes
06:00 | Final health check — all env vars, DNS, Sentry, Supabase | Founder | pending | No code changes after this
07:00 | Send waitlist email: 'We're live' | Founder | pending | Pre-written Resend template
08:00 | Daily digest test send (check 1 real user) | Founder | pending | Verify cron fired
09:00 | Publish LinkedIn launch post (authentic founder voice) | Founder | pending | Pre-written, proof-read
10:00 | Post to X / Twitter (secondary) | Founder | pending | -
11:00 | Share in 3 UAE expat Facebook groups (organic, not spammy) | Founder | pending | -
13:00 | Monitor Sentry + Supabase + Vercel logs | Founder | pending | Every 15 min
14:00 | Respond to every signup email manually (concierge onboarding) | Founder | pending | First 50 users = VIP
15:00 | Confirm first Office Hours session for May 4 | Founder | pending | Calendly link live
16:00 | Rotate through any bug reports | Founder | pending | Fix critical, defer cosmetic
18:00 | Final user count + MRR snapshot | Founder | pending | Target: 50 signups by 18:00
19:00 | NO CODE CHANGES AFTER THIS. Founder dinner. | Founder | pending | Hard rule
22:00 | Bed | Founder | pending | Tomorrow is day 2

## Team
Role | Person | Responsibilities | Phase | Hours/Week
Founder / CEO | Inspire Ambitions | All of it: product, code, customer discovery, marketing, support | Phases 0-5 | 60+
Engineering contractor | TBH Month 6-9 | Scraper maintenance, ATS adapter upkeep, infra | Phase 5+ | 15
Content marketer | TBH Month 9-12 | Organic SEO, LinkedIn, UAE expat community | Phase 5+ | 10
Legal advisor | External UAE lawyer | PDPL review (2-hour engagement in Phase 3) | Phase 3 | One-off
Accountant | Not needed Year 1 | - | - | -